## Mchinji
Analysis of material support provided by the Mkanda project - 2026
Date of update: 6/2026
Date | Area or facility | Support provided | Comment on what was done (method, community contribution, difficulties, etc.) | Cost (expected vs done, in MWK and EUR) | Current status (usage, functionality, maintenance, etc.) | Assessment of impact (was it effective in its objective, was it durable, should we have done it or not, what could have been done better, etc.)
2023-09-01 | Mkanda HC | Water system maintenance | Pipes were changed and realigned, and water tanks were replaced. |  | Functional | Improved water availability and reliability at the facility. It was necessary to do it. It improved hand washing and cleanliness, thereby reducing transmission of disease causing microorganisms, making the facility a safe place
2023-09-01 | Mkanda HC | Emptying the placenta pit | A contractor was hired at a cost of MK1,000,000. |  | Requires maintenance; placenta pit is full again. | We provided a safe disposal site for remains of conception products (waste), thereby creating a safe place for facility users and the community. It was necessary doing it, as proper disposal of waste minimises spread of diseases among the health facility workers and communities close to the facility. The emptying of the pit is cheaper than constructing a new placenta pit. However, eventually the pit will be full again, making the process ongoing
2023-11-01 | Mkanda HC | Installation of solar-powered power bank for maternity | Installed to support the opening of the new maternity building in January 2024. |  | Not functioning; batteries need replacement. | The provision of back up lights in the labour ward made it easy for the staff to operate during the period that the power from national grid goes off. It was necessary to make sure the midwives continued to provided quality services, thereby saving new born lives and the women. The sustainability of the back up lights depends on proper maintenance and timely replacement of batteries.
2023-11-01 | Mkanda HC | Borehole maintenance |  | Maintenance carried out at a cost of MK8,000. | Functional | The borehole works as a back up for the facility when there is no water, due to power outages. The maintenance has therefore guarantee water availability at the facility as well as the labour ward when the pumps run dry due to power outages. The sustainability of this support requires the involvement of the key stakeholders eg the HAC. At Mkanda, the HAC is involved and committed, reassuring that the borehole will remain functional over the years ahead
2023-11-01 | Mkanda HC | New maternity water system maintenance |  | Payment for materials and maintenance amounting to MK65,900. | Functional | We reconnected the water supply into the new maternity, which remained unused since around 2018 when it was handed over to Mchinji DHO. The water reconnection was part of the maintenance of the new maternity for the DHO to open it. It was therefore necessary as the new maternity is now open, with running water and services are being provided.
2023-11-01 | Mkanda HC | Facility water tank maintenance |  | Maintenance conducted at a cost of MK43,000, including materials. | Functional | Improved water storage capacity at the facility therefore, making sure of constant water supply at the facility
2023-12-01 | Mkanda HC | Completion of two staff houses |  | Labour cost MK5,891,800 and materials MK17,379,012; contractor: Mitundu. | In good condition | It was effective. We addressed accommodation challenges for staff and again, improved staff retention as the houses are nice and the Officers do not want to leave.
2023-12-01 | Mkanda HC | Maternity equipment provision | Supplied soap, buckets, mops, comb removal tools, and brushes. |  | All equipment in use | Improved availability of essential maternity equipment and promote cleanliness of the facility inside.
2024-01-01 | Mkanda HC | Maternity mobile phone | Phone provided to support referrals. |  | Phone missing since Nov 2024 | The phone eased the communication between Mkanda HC and Mchinji District Hospital, mainly when there is a referral case. Through the phone, the Officer on duty would call Mchinji hospital for an ambulance, and at the same time, informing them of the case to be referred, so that Mchinji prepares. The initiative works better where there are good controls and committed staff. The phone got stolen in November 2024, about a year after we donated
2024-02-01 | Mkanda HC | New maternity plumbing and curtains | Payment made for plumbing works and 12 pieces of 2‑metre curtains. |  | Functional | This was part of the maintenance of the new maternity so that we can open it. The support facilitated the opening of the new maternity ward, after about 5 years of being used as a hostel for staff and other people.
2024-03-01 | Chimwamkango HC | Transport support for pregnant women |  | MK16,000 paid to support transport to Mkanda HC. | Initiative was stopped | The objective of the initiative was to support poor pregnant mothers with money for transport to go and deliver at Mkanda HC, thereby reducing home deliveries and protect them from harsh penalties from the chiefs once they give birth in the village. The initiative did not succeed due to abuse by the HC staff, who were mandated to select and refer beneficiaries to Mkanda HC. The initiative was temporary, to run for 2 years until the Gumba maternity opens. We could have left the initiative in the hand of Inter Aide for it to succeed. Currently, Last Mile organisation from Lilongwe is introducing the same in the catchment. They will be using the community structures and HC staff. We will learn from the once they role it out.
2024-03-01 | Gumba HC | Transport support for pregnant women |  | MK352,000 paid for 22 women (MK16,000 per woman). | Initiative was stopped | As above
2024-04-01 | DHO | Measles campaign fuel | Fuel provided for outreach activities. |  | Completed | The campaign increases mass coverage of U5 children vaccinated with the measles vaccine. It is effective and must continue
2024-04-01 | Mkanda HC | ESCOM fees for two staff houses |  | Paid MK150,000. | Electricity available | Improved living conditions for staff.
2024-06-01 | Mkanda HC | 1,000 partographs | Procured for maternity documentation. |  | In use | Improved labour monitoring and record‑keeping.
2024-06-01 | DHO | 3,000 partographs | Distributed to health facilities. |  | In use | Improved labour monitoring and record‑keeping, therefor enhancing quality service
2024-09-01 | Gumba HC | Rehabilitation and water installation | Maintenance of the walls, floor , painting, putting new doors, windows and glasses, installing electricity and water and sanitary facilities. The works were completed in Nov 2024. |  | In good condition | The maintenance has put back the shape of the HC, making it suitable for providing health care services. The centre has running water, electricity and in good condition now. The building was dilapidated and the maintenance was necessary to keep it in good shape
2024-09-01 | Mkanda HC | ESCOM units | Electricity units purchased at a cost of MK20,000. |  | Adhoc support | Ensured continuity of electricity supply so that the staff work in light and run services even at night.
2025-01-01 | DHO | Diaries to DHO team | Three diaries provided to the QI team. |  | In use | For planning and records. Not sustainable and stopped
2025-02-01 | Gumba HC | ESCOM fees and chairs | Electricity fees paid and two chairs provided. |  | Chairs in good condition | The lights make is easy and comfortable for the Health Workers to attend to cases even at night, while they sit on comfortable chairs. This support is sustainable and more impactful, because it has motivated the Health Workers to work more and comfortably
Feb–Dec 2025 | DHO | Fuel for drug distribution | Monthly fuel support | (MK400,000–MK410,000). | Program working | Addressed drug shortages caused by transport challenges. The Mchinji DHO uses this fuel to collect drugs in Lilongwe and distribute it in the HCs, making sure that drugs are available and minimises stock outs. The support has contributed positively, as drug stocks in the HCs did not deplete after USAID phased out in 2024. However, it is not sustainable but necessary
Mar & Apr 2025 | DHO | Nursery forms photocopying | Payments made for photocopying nursery forms. |  | Ongoing based on needs | For case admission notes and monitoring of care and progress. It is necessary for documenting and tracking progress for each patient. It is a critical support to the Hospitals which are working in resource constrained environment, to adhere to standard treatment procedures
2025-04-01 | Chimwamkango HC | Furniture donation | Four chairs and two tables donated. |  | In use | Addressed equipment shortages and improved staff motivation to discharge their duties. The staff now sit on comfortable chairs. The support is sustainable and necessary
2025-05-01 | Gumba HC | BP machine batteries | Batteries supplied for BP machine. |  | Functional | Improved the monitoring of women who attend antenatal services and other reproductive health services. The assessment of blood pressure is key to assessing the health of the mother therefore, the donation of the BP machine is necessary for the best care to the women who seek services at this centre
2025-06-01 | Mkanda HC | BP machine donation | One BP machine donated to maternity ward. |  | Functional | As above
2025-08-01 | DHO | Stationery and forms support | Admission forms (MK120,000), partographs (MK200,000), paper and pens. | Admission forms (MK120,000), partographs (MK200,000), paper and pens. | In use | As above; for monitoring of care for inpatients. Very necessary as case monitoring and documentation is part of providing quality care.
2025-08-01 | Mkanda HC | Maternity shelving |  | Shelf installed at a cost of MK15,000. | Functional | Improved storage of essential medicine and organization. Very important aspect for urgent treatment and care in labour wards. It was necessary doing it
2025-09-01 | Multiple HCs | Stationery support | Pens and papers distributed to facilities. |  | In use | For documentation. It supported daily service delivery, therefore, necessary but not sustainable.
2025-09-01 | New clinics | Basic equipment support | Cups, spoons, drug boxes, water buckets, locks, and basins supplied. |  | In use | The donations assisted in opening of the vg clinics, otherwise, the clinics couldn’t open. The donations ae key for the operation of the vg clinic, to treat U5 children, making the service sustainable
2025-11-01 | Gumba HC | Construction of Gumba maternity | Construction works initiated. |  | Ongoing | Expected to improve access to maternity services.
2025-12-01 | Fanuel HC | Adult weighing scale | Adult weighing scale provided. |  | Functional | Improved patient assessment and monitoring.

## Mitundu
Analysis of material support provided by the Mitundu project - 2026
Date of update: 6/2026
Date | Area or facility | Support provided | Comment on what was done (method, community contribution, difficulties, etc.) | Cost (expected vs done, in MWK and EUR) | Current status (usage, functionality, maintenance, etc.) | Assessment of impact (was it effective in its objective, was it durable, should we have done it or not, what could have been done better, etc.)
2014-07-01 | Katchale | Donated 6 mattresses, 24 bedsheets, 6 blankets, 6 bed nets, 1 new-born resuscitator bed, 1 BP machine, 1 baby weighing scale, 1 vacuum extractor, 1 wall clock | These items were donated to Katchale HC, to improve service delivery and comfort to clients |  | Most item are in use. Some mattresses need replacement because they are too torn. | Improved quality of maternal and new-born care; However, this is not sustainable. Currently the mattresses are too torn to use. In the future, the support should include a replacement and maintenance plan, done after a specific period of time.
2014-07-01 | Mitundu Hospital | Donated 1 wall clock, 2 reams of paper, 2 electric power cords, 1 electric heater | The donation was for the opening of the kangaroo mother care room |  | In use. | Supported daily operations and documentation. The donation was effective for service delivery and saved lives, mainly in the kangaroo room where premature babies are managed. It was a sustainable initiative
2014-08-01 | Katchale | Construction of Khuzi Village Clinic |  | Estimated budget was MK 2,184,250 but actual cost was MK 2,884,250 for the house; VC shelter cost MK 2,361,350. | Functioning. The structure is turned into a Health Post. The roof is badly damaged by termites and need maintenance asap | Improved access to diagnosis and treatment for U5 sick children and improved the primary health care services eg vaccination. The village clinic is still in operation now but the structure needs maintenance. We learn a lesson and best practice at this construction. In the following vg clinic construction, we modified the construction approach, where Inter Aide paid 20% of the construction materials, so that the community should own and maintain their structure. The Khuzi clinic is in dilapidated state and the community is coming back to Inter Aide requesting for assistance to maintain it.
2014-10-01 | Maluwa | Water tank | Installed to improve water availability at the facility. |  | Functioning. | Improved water access; essential for infection prevention and quality service delivery.
2015-07-01 | Katchale | Solar lighting system installation | Installed to address lack of electricity. |  | Functioning. | Improved service delivery, made sure that services are also available at night; sustainable and appropriate intervention.
2015-07-01 | Katchale | Water system rehabilitation | Rehabilitation works conducted to restore water supply. |  | Functioning. | Addressed chronic water shortages; regular maintenance recommended.
2015-07-01 | Katchale | Construction of 1 nurse house and renovation of the MA house | The construction of the Nurse house was a community managed project; whereby the community contributed bricks and sand | The budget was MK 2,691,000. | Functioning. | Improved staff motivation and retention by providing accommodation; highly relevant intervention and sustainable. However, the house is now occupied by the Medical Assistant In-charge, as it is the only big and beautiful house at the facility.
2016-06-01 | Maluwa | Water system rehabilitation | Connected water into the facility, replaced old pipes with new one. Maintained the heavily leaking water tank |  | Functioning. | Improved water availability for the facility, for the continued service delivery; durable intervention.
2016-06-01 | Maluwa | Solar lighting system installation | Solar system installed for lighting. |  | Functioning. | The donation answered the challenge for lights, necessary for the Providers to provide care at night. It was effective and made sure for the continuity of services, even at night
2016-09-01 | Maluwa | Construction of 2 staff houses | 2 houses were constructed to address staff accommodation gaps | with a budget of about MK6,000,000, using the community managed approach. | Functioning. | Effective. The donation provided enough staff accommodation, thereby increasing number of staff who are motivated and stay longer. Since then, Maluwa HC has had enough staff for the continuity of services
2016-11-01 | Maluwa | Renovation of maternity waiting home | We put in a new roof and iron sheets |  | Functioning (but not as MWH) | Effective. The donation answered to the issue of accommodation for the pregnant women who come to wait for labour. The women who wait for labour at the facility are monitored and assessed on time by the Midwife, thereby preventing complications that might have happened either to the mother and the foetus or new-born baby if they delayed. However, in Maluwa, the MWH has been seldom used by women, who are advised to stay in the maternity (usually not crowded). The renovated room is used for other purposes for the HC.
2018-01-01 | Dickson | Construction of 1 MA house | Constructed a house with support from the community, | with an estimated budget of MK7,000,000 | Functioning. | Improved staff numbers and retention, for better service delivery.
2018-02-01 | Mitundu Hospital | Creation of a nursery ward by partitioning the current main NRU | Partitioning done to create a dedicated space for at-risk new-borns following audit findings. |  | Good condition and functioning. | Improved the care and management of sick or premature new-born babies; thereby preventing death to many new-born babies
2019-08-01 | Dickson | Construction of N'gombe and Chidangwe VCs (+ HSA house) | We provided funding for the construction of the HSA house and a shelter at N'gombe and a shelter at Chidangwe. We provided labour fees to the Builders, iron sheets, cement, doors, windows and painting. The community provided the bricks and casual labour, including digging and construction of latrines |  | Structures available but underutilized. The HSA house at N'gombe is vacant after the HSA Provider left. He is operating from Mitundu. The Shelter at Chidangwe is not being used, the Provider retired and has not been replaced. The support was effective, but difficult to sustain. We relied on the motivation of HSAs and the leadership that were there at the time of constructing these shelters. Currently, the reinforcement by the HSAs Managers is absent and the shelters are not being fully utilised. | Infrastructure exists but utilization is low; stronger follow-up and staffing required.
2019-10-01 | Dickson | Extension of maternity ward | We increased the size of the labour room to accommodate 4 beds from 2, and created structures for antenatal and family planning services, Midwife office and sanitary facilities for both staff and clients, including the sluice room | with an estimated budget of MK15,000,000 | Functioning. | The donation was effective. It improved the labour room space, enabling free movement of the Midwife to provide best care as sometimes, all 4 beds are occupied at the same time. The donation also made available spaces for antenatal and family planning services. The new maternity is also a motivation for women to give birth at this place and also a motivation to the Midwives. For example, Mr Ginty, a Midwife is refusing to be transferred from Dickson HC, because he is happy with the structure. He was there when the project kicked off
2020-04-01 | All HCs and Mitundu Hospital | Buckets and soap (COVID-19 response) | Distributed to all HCs as part of improving hand hygiene and infection prevention measures during the Covid-19 pandemic. |  | Soap used; buckets still functional. | Effective short-term IPC response; consumables require replenishment.
2020-08-01 | Maluwa | Installation of solar water pump | Lilongwe DHO provided power cable (~MK 200,000); Inter Aide contributed MK 2,579,250. | Lilongwe DHO provided power cable (~MK 200,000); Inter Aide contributed MK 2,579,250. | Functioning. | Long term support. We addressed the water challenges at Maluwa HC.
2020-09-01 | Chioza, Chiunjiza, Dickson | Drug boxes to village clinics | Drug boxes supplied to vg clinics to improve drug storage. |  | Functioning. | Improved drug safety and organization for the running of the village clinics. Effective and sustainable
2021-01-01 | Maluwa | Chairs, table and drug box for Sere VC | Donated furniture to village clinics to enable them open |  | Not functioning since 2021. remained with 1 chair, table and drug box | The support was appropriate and timely for the opening of the new village clinic at Sere. However, the Provider left and was not replaced ever since, making the support ineffective.
May 2020 | Maluwa, Katchale, Dickson | solar kits, electrification | Electrified the HCs jointly with the Lilongwe DHO (shared costs) to bring electricity in the HCs, to improve service delivery and provided solar torches for back up |  | Functioning. | Improved general service delivery, waste management, lighting, and motivation of staff. Effective and sustainable
May 2020 | Mitundu Hospital | Installation of submersible pump | We bought and donated a submersible pump to Mitundu Community hospital, after the facility's pump got stolen and there was a crisis because of no water. The services were suspended. | The Pump costed MK 2,450,000. | Functioning. | Effective and sustainable investment. The availability of water at the hospital made sure that services continued and not disrupted.
May 2020 | All HCs in Mitundu | Cholera response supplies (chlorine, buckets, boots, toilets) | Emergency response interventions. |  | Used. | The cholera response kits were effective against the further spread of cholera, mainly in the facilities where sanitation and hygiene is poor due to overcrowding
May 2020 | Chadza | Village clinic shelter construction and power banks | We supported the construction of village clinic shelters with roofing materials, | that costed MK 2,994,000. | Functioning. | Effective and sustainable. The shelters are a prerequisite for the running of the village clinics, thereby bringing the health services closer to the people for easy access
May 2020 | Maluwa, Katchale | Water system maintenance | Donated materials for water system maintenance and paid for labour |  | Functioning. | Prevented further system breakdown that would become too expensive, and at the same time, made sure that the water continues running in the HC for general service delivery
May 2020 | All HCs in Mitundu | Documentation materials (hard covers, diaries, pens, paper) | Provided stationery to support reporting on DHIS2, planning and general documentation to keep records |  | In use. | Strengthened data quality, reporting, and accountability.
May 2020 | Chiunjiza, Chioza | Curtains and hard covers for maternity wards | Donated curtains to improve privacy and documentation in the labour wards. |  | Curtains available and in use. | Improved privacy and dignity during labour; low-cost, high-impact support.
May 2020 | Dickson | 120 reusable face masks | Covid 19 response |  | Depleted | Helped to reduce the transmission of Covi-19 during the time. Short time support and not sustainable
Sep 2020 | Chioza | Drug box to Mliu Village Clinic | Donated the drug box, to facilitate the opening of the village clinic. The drug box is one of the critical equipment needed to open new village clinics |  | Functioning | To enable the opening of the vg clinics, drug storage and safety. An effective support and sustainable.
Sep 2020 | Chiunjiza | Drug box to Mthenga Village Clinic | Donated the drug box, to facilitate the opening of the village clinic. The drug box is one of the critical equipment needed to open new village clinics |  | Functioning | To enable the opening of the vg clinics, drug storage and safety. An effective support and sustainable.
Sep 2020 | Dickson | Drug box to Kalesi Village Clinic | Donated the drug box, to facilitate the opening of the village clinic. The drug box is one of the critical equipment needed to open new village clinics |  | Functioning | To enable the opening of the vg clinics, drug storage and safety. An effective support and sustainable.
Nov 2020 | Maluwa, Katchale, Dickson and Chiunjiza | We bought and donated 1 BP machine to each of the facilities; Maluwa, Dickson, Katchale & Chiunjiza HC) |  | We bought the machines at 89, 000.00 | Not functioning, they are damaged | The donation was effective in the assessment and monitoring of pregnant women and those in labour, for their well being and the well being of the foetus. The machines are damaged and not in use. The DHO is not replacing the damaged machines nor replacing the batteries, making the donation effective but not sustainable Improved the management of women attending antenatal and those admitted in the labour ward. Needed to put a plan for replacing batteries, otherwise, it is not sustainable and ineffective when the batteries are not being changed and the damaged machines are not being replaced
Dec 2020 | Chadza | Rehabilitation of water system | We maintained the water system at Chadza, replacing old broken pipes and installing new ones. | The work costed MK 322,300 for materials and labour MK 75,000. | working | Effective and sustainable support for the continuous running of water in the HC, for the general service delivery
Dec 2020 | Maluwa | Donation of a used motorbike (BP 7982) | Not available |  | Not working | The donation was to respond to transport challenges, to enable the staff of Maluwa to independently pick drugs and other essentials at Mitundu hospital, about 20 Kms to Maluwa, and make sure services are not disrupted due to drug shortage. Again, the bike was to assist the Senior HSAs conduct supervision of the community health activities in the catchments, including supporting the U5 health outreach clinics. The donation was ineffective and not sustainable. The HSAs stole parts of the bike and there was no leadership to sustain the bike. It is a lesson and we will never do it in the future
Dec 2020 | Chiunjiza | Louver glasses fixing |  | Costed MK25, 830.00 | Available | Responded to issue of privacy in labour ward
Feb 2020 | Chiunjiza | 6 Chairs & 3 Tables to Kampambanya, Kuphunda & Kunchetsa village clinic- 2 chairs each clinic and 1 table per clinic |  |  | Available , Kumchetsa village clinic not functioning, no provider | Responded to issue of equipment
Jan 2021 | Maluwa | 2 Chairs, table and drug box( Sere & Chikumba village clinic) |  |  | Clinics not functioning since 2021 but the equipment are still available at Chikumba Village clinic whilst Sere village clinic, 1 Chair, table and drug box are still available | The donation was essential and made it possible for the opening of these new village clinics mentioned. However, due to leadership challenges affecting the Environmental department of our Health System, the HSA Providers were not replaced, after the initial HSAs who were trained and opened the clinics got transferred to other HCs
Feb 2021 | Katchale, Maluwa, Dickson, Chiunjiza, Chioza and Mitundu hospital | Donated 6 phones to help with referrals of emergencies (+ credit) | The phones were donated to improve communication. Every month, the facilities received airtime of MK2000 for making communication. The airtime has been provided since 2022. We stopped in January 2026 after making assessments to establish the phones that are still available. |  | Phones missed | The donation was effective initially by improving the communication between the HC and Mitundu but needed strict monitoring of the measures we put in place to track the phones usage. Due to lack of this, the phones got stolen by the HC staff. The Mitundu Management failed to track and arrest the one who stole the phones. With the many lessons we have got from this initiative, it is not sustainable at all, though it is effective.
Apr 2021 | Chiunjiza | Electrification of 4 staff houses |  | Lilongwe DHO contributed MK350, 000.00 and Inter Aide contributed MK390, 650.00 | working | Effective and sustainable. We have also demonstrated that sometimes, joint investment works with the best collaboration
Apr 2021 | Katchale | Incinerator construction | Funded for the construction of the placenta pit and incinerator. The communities provided sand and soakway stones |  | Functioning | Effective and sustainable. We improved the waste management at the facility to reduce the spread of disease among hospital staff, users and the general community
Apr 2021 | Maluwa | Incinerator and placenta pit construction | Funded for the construction of the placenta pit and incinerator. The communities provided sand and soakway stones |  | Functioning | Effective and sustainable. We improved the waste management at the facility to reduce the spread of disease among hospital staff, users and the general community
Apr 2021 | Dickson | Placenta pit construction | Funded for the construction of the placenta pit. The communities provided sand and soakway stones |  | Functioning | Effective and sustainable. We improved the waste management at the facility to reduce the spread of disease among hospital staff, users and the general community
Apr 2021 | Dickson | Rechargeable torch to Kamphoni Village Clinic | Donated a solar chargeable torch |  | Functioning | Effective. The torch enables the Provider to attend to U5 cases even at night, as he stays in the catchment.
Apr 2021 | Mitundu hospital | Autoclave | We funded for the purchase of the Autoclave, that the Operating Theatre at Mitundu uses to sterilise large volumes of equipment and materials. | We paid MK300, 000.00 | Functioning | The donation helped to cut costs and save lives. Initially, after the autoclave got broken, the cases needed surgical operations were being referred to Lilongwe for operations; something that increased the delay to provide care, as sometimes the transport might not be available
Apr 2021 | Chioza | Solar power torch | We donated a solar torch, | that costed MK34, 000.00 | Functioning | The donation was effective and sustainable. Provides light in the labour ward when power from the main grid goes off, making sure that the Midwives continue working
Apr 2021 | Chioza | 2 Chairs and table - Mazinga Village Clinic | We funded for the procurement of 2 chairs for Mazing vg clinic, to improve comfort for the guardians and the Provider |  | Functioning | Effective. The chairs are used by Provider and clients
Apr 2021 | Dickson | Incinerator Renovation | We funded for the maintenance of the incinerator. This was cheaper as compared to constructing a new one | costed us MK173, 000.00. | Functioning | We improved waste management at the facility, to reduce risks of disease contamination
May 2021 | Dickson | Installation of solar power for N'gombe VC and Chidangwe VC (+HSA house) | We donated solar panels and a battery | that costed MK155, 000.00 in total | Not function. The solar panels are believed to have been stolen by the HSA who was residing at the site | We wanted to improve the motivation of the vg clinic Provider, and to also for the fact that the Provider was staying at the site, he would have been seeing cases even at night.
May 2021 | Chioza | 3 buckets | We donated water buckets at Chioza maternity, to store water for emergencies when water stops running |  | Not available | The donation temporary saved the purpose. However, it is not sustainable. The buckets are broken and damaged, need to be replaced over time
May 2021 | Dickson | 3 buckets |  |  | Not available
Jun 2021 | Maluwa, Katchale, Chiunjiza, Dickson, Chioza | 5 sharps waste bin | We donated sharps bin, to improve waste management. | It costed MK80,000.00 | Not available | The bins are damaged and no longer in use. Effective for a [period of time. Needed to be replaced over a period of time
Jul 2021 | Chadza | 1 table, 2 Chairs, 2 Tap buckets, 2 Basins, 2 Cups, 2 Spoons and drug box(Mnjolo & Kachitsa Village Clinic) | Donated for the opening of the new vg clinics |  | Functioning | Effective and sustainable for the running of the vg clinics. The clinics are still running
Jul 2021 | Katchale | 1 table, 2 Chairs, 2 Tap buckets, 2 Basins, 2 Cups, 2 Spoons and drug box(Namikango & Mdabwi Village Clinic) | Donated for the opening of the new vg clinics |  | Functioning | Effective and sustainable for the running of the vg clinics. The clinics are still running
Aug 2020 | Chiunjiza | 2 Chairs and table( Ben Village clinic, Chewire & Mbiriyaundi | Donated for the opening of the new vg clinics |  | Ben and Che wile clinics closed because of the opening of new Ben HC, opened in 2025. Mbiriyaundi vg clinic closed since the Provider transferred. There is no replacement yet | The donation was effective for the opening of the vg clinics.
Sep 2021 | Dickson | Gas cylinder and gas burner | We donated the gas cylinder and burner for the sterilisation of the delivery kits, after their electric steriliser was damaged |  | Available | Effective. The gas cylinder is still functioning
Nov 2021 | Chiunjiza | 100 bags of cement | Contributed towards the fence construction project | Costed MK1, 000.00 | used | The construction of the fence did not complete. It was heavily relied on donors and the community through HAC failed to sustain it. Not effective. We could have waited and support the construction whilst midway before completion
Nov 2021 | Chiunjiza | Fluorescent tubes |  | costed MK10, 398.00 | Functioning | To provide enough lighting in the labour ward. Effective and sustainable
Nov 2021 | Chadza | 2 door frames | We donated 2 door flames, for the construction and maintenance of the facility latrines | costed MK19,000.00 | functioning | Improved sanitation at the HC. The doors offered privacy to the users of the latrines
Dec 2021 | Katchale | 2 Delivery Mattresses | We donated 2 delivery mattresses for the Katchale labour ward, | that costed MK131, 398.00 | Currently, the mattresses are too torn to be used; still functioning | Effective but not sustainable. Need to replaced over time and based on condition
Nov 2021 | Chadza, Katchale, Chiunjiza | Supported 5 village clinics shelters with roofing materials(Mwadzungu clinic under Chadza HC, Namikango Clinic under Katchale HC & Chamkoma as well as Kuphunda under Chiunjiza Health Centre). |  | Costed MK3, 529, 860.00 | Clinics are functioning | Effective and sustainable for the running and continuation of the clinics
Feb 2022 | Chioza | Building of 1 nurse house | We built a Nurse house at Chioza, using the community managed approach. | The house costed 5, 332, 000.00 | functioning | Responded to staff houses shortage and retention. The Nurse Midwife who occupied this house is still there and motivated. Effective and sustainable initiative for continuation of service delivery
Feb 2023 | Chiunjiza | Renovated the ceiling of the HC |  | Costed MK678, 710.00 | Still exist | Improved the outlook and safety of the structure and minimized further damage to the roof. Again, the old ceiling parts that were falling due to ageing poised a danger to the staff and clients. The maintenance was therefore effective
Feb 2023 | Chadza | Funded the construction of the new latrine at Chadza HC, part of the 2023 Inter Aide cholera response | The work was not community managed, i.e. Inter Aide funded 100% of the construction budget | We paid MK581, 200.00 for materials and labour. | Functioning | Improved sanitation at the HC by providing privacy
Feb 2023 | Chadza | 20 litres bucket of chlorine and 6 gumboots | Donated Cholera kits, as a response to the cholera outbreak in Chadza |  | used | Effective and contained the spread and management of cholera
Feb 2023 | Chiunjiza | Solar lamp backup - Maternity | Donated a solar chargeable torch to be used as a backup when there is no power |  | Not available | Effective but not sustainable due to poor management and lack of effective leadership to safeguard the HC materials and equipment condition
Feb 2023 | Dickson | 2 Room rocks - OPD and Maternity | For the maintenance of the doors, for privacy |  | Available | To control entry and keep the labour wr/maternity private
Feb 2023 | Chadza | Placenta pit empting |  | Costed MK1, 000, 000.00 | Functioning | Response to waste management
Mar 2023 | Chiunjiza, Maluwa, Katchale & Dickson | 20 Litres Chlorine- Cholera response | Donated cholera kits for facilities, for cholera prevention and control |  | Used | Response to Cholera outbreak. Was effective to contain the outbreak
Apr 2023 | Maluwa | 2 Room rocks - OPD and Maternity | Donated the rocks, part of the facility maintenance, targeting critical rooms only to safeguard medicines and other important supplies and enhancing privacy |  | Functioning | Effective. HC doors maintenance is one of the important aspect to keep the structure in shape and minimise theft and entry into the private or secure rooms
Apr 2023 | Chiunjiza | Room rock for Kampambanya Village Clinic | Donated rim-rocks, to keep the vg clinic rooms secure |  | Functioning | For security of drugs and other essentials
May 2023 | Katchale | Donated building materials and paid for labour fee for the construction of Namikango Village clinic | Bought Lime and bags of cement | that costed MK295 700 and paid for labour of MK260 000 . | Functioning | Effective as the village clinic structure is still being used and in good shape
Sep 2023 | Maluwa | 3 Energy saving bulbs | Donated bulbs for lights |  | Used | This is the kind of little support that the DHO authorities fail to provide to the health centres, and that frustrates service delivery. It is effective but not sustainable, as it has to be replaced over time
Oct 2023 | Chioza | Construction of a fence, Incinerator |  | The works costed MK109, 000 for materials and MK52, 000 for labour | In use. | Effective in keeping the waste site secure from children and others, and prevent getting secondary infections
Nov 2023 | Katchale, Maluwa, Dickson, Chioza and Chadza | Donated and installed power banks in the HCs |  |  | not in use | Need to replace batteries. Effective but not sustainable as batteries need to be replaced every year. In Dickson, the batteries were stolen
Nov 2023 | Maluwa | Re-electrification works | This is after the Malawi Power Supply Company disqualified the wiring for Maluwa HC, the work that was supported by Inter Aide in 2021. | Whole work costed MK305, 900. | Functioning | Effective. We also learned that cheap labour is mostly dangerous, as the works in Maluwa was done twice. It is alleged that the one we hired in 2021 was not happy with the negotiated amount we paid him.
Dec 2023 | Maluwa, Katchale | Fixed and maintained the water system at Maluwa and Katchale Health Centres respectively. |  | MK385, 000 for materials and labour fee of MK115, 000 for Maluwa Heath Centre and MK110, 000 for Katchale Heath Centre. | Functioning | Water system maintenance is crucial in making sure of disrupted water supply in the HCs. The system at both Maluwa and Katchale frequently breaks down because of the abuse by the community members, who use these water points for their hhs use
Feb 2024 | Maluwa, Katchale | Supported BP Machine and batteries | Donated 1 BP machine to each, Katchale and Maluwa HCs |  | Functioning | Effective for quality assessment and monitoring of mainly women attending antenatal care and those in labour
Feb 2024 | Chioza | Water system maintenance | Paid for the water system maintenance |  | Functioning | effective for making sure water is available at the HC throughout
Feb 2024 | Katchale | Support of hard cover for report book at maternity | Donation of essential stationery, key to improving patient care through record keeping |  | Used | The hardcover exercise book is finished now, need to be replaced. Effective but not sustainable, as it relies on the donor support
Feb 2024 | Dickson | Support of hard cover for report book at maternity | Donation of essential stationery, key to improving patient care through record keeping |  | Used | The hardcover exercise book is finished now, need to be replaced. Effective but not sustainable, as it relies on the donor support
Feb 2024 | Chiunjiza | Support of hard cover for report book at maternity | Donation of essential stationery, key to improving patient care through record keeping |  | Used | The hardcover exercise book is finished now, need to be replaced. Effective but not sustainable, as it relies on the donor support
Jun 2024 | Mitundu hospital | 8 Diaries Support to quality improvement team and 1 hard cover for maternity | Donated 1 Diary to each of the QIT members, for planning and keeping records |  | Used | Helped on planning and keeping key notes of their findings during the visits to the HCs. However, this is not sustainable
Jul 2024 | Mitundu hospital | Donated 1 box of pens and 2 hard covers | We give stationery every 2 months for documentation and records, an ongoing support |  | Used | The stationery helps the facility on documentation and record keeping, for case monitoring
Se 2024 | Mitundu hospital | Donated fuel for the data Officer (HIMS) to support the HC Data quality sessions | Paid for Fuel, that costed 104,000, for the Mitundu Health Area car for the Officer to go to all 6 health centres (Maluwa, Katchale, Chiunjiza, Dickson, Chioza & Chadza) |  | Used | The quality of the HC data has improved
Oct 2024 | Mitundu hospital | Donated hard cover exercise book for report book at maternity | We donated a hard cover exercise book to Mitundu Hospital maternity for record keeping |  | Used | Records are kept for reference and monitoring of cases
Jan 2025 | Mitundu hospital | Donated 6 diaries to Mitundu Management Team and the QIT | Donation of diaries |  | Used | The donation improved planning and record keeping
Mar 2025 | Mitundu hospital | 1 BP machine and 28 batteries for Health centre thermometers. Paper ream and box of pen support, | Donation of medical equipment and stationery |  | In use. | Improved the quality service delivery, through best assessment and monitoring and record keeping
Apr 2025 | Dickson | Donation of vital stationery | Donated a hard cover exercise book to Kalesi and Kaphoni village clinics to document and keep daily opening records |  | Used | Improved the opening of the village clinics
May 2025 | Mitundu hospital | Door maintenance and replacement of bulbs at Mitundu Nursery ward | We donated 3 rimslocks and bulbs as part of maintenance of the Mitundu Nursery ward |  | Fixed | The Nursery ward is maintained and in good conditions, lights are available to enable Officers do their job even at night
May 2025 | Chadza | Funded the maintenance of Chadza HC roof | We donated the roof sealing kits (that costed us MK30,000) to Chadza and provided transport (bike) to the Maintenance Officer from Mitundu to fix the leaking roof at Chadza HC |  | Roof fixed | The roof is no longer leaking, provided a better environment for service delivery
Jul 2025 | Dickson, Katchale | Donated hard cover exercise books to Kalesi and Kaphoni village clinic in Dickson and Chimphanga in Katchale . | The exercise books are for record keeping on opening days, kept by the Volunteers and signed by the Provider when the clinic opens |  | In use. | Improved vg clinic opening days tracking
Jul 2025 | All HCs in Mitundu | Funded the maintenance of the HCs by replacing locks, mainly in critical rooms where they keep drugs and also where privacy is needed | Donated roomlocks, 2 to each facility |  | Doors were maintained and rooms made secure | The donation improved the security of the rooms and privacy
Jul 2025 | Chioza | Donated a hard cover exercise book to Chalera village clinic | The exercise books are for record keeping on opening days, kept by the Volunteers and signed by the Provider when the clinic opens |  | In use. | Improved vg clinic opening days tracking