## Phalombe
Analysis of material support provided by the Phalombe project - 2026
Date of update: 06/2026
Start date | Handover date | Area or facility | Support provided | Cost MKW | Cost euro (conversion with rate of the construction year) | Comment on what was done (method, community contribution, estimated budget, duration of work, difficulties, etc.) | Current status (usage, functionality, maintenance, etc.) | Assessment of impact (was it effective in its objective, was it durable, should we have done it or not, what could have been done better, etc.)
June 2016 |  | Nambazo HC | Construction of a maternity waiting home |  |  | Community participation was really impressive as they contributed with burnt bricks, sand and big stones for laying of foundation. Issue on contractors because the first contractor disappeared when he was about to start digging the foundation, so the contract was given to another contractor who started digging and cconstructed and finished the whole foundation. But then he disappeared before raising the wall, because he realised he underestimated his quotation. After that the contract was now given to the third contractor who started construction from the foundation level up to the finishing of the whole building (roofing, glass and door fittings, painting). The HCMC provided the store room for storing the construction materials just within the Health Center premises. | The maternity home is functional and being utilised by the community to wait for delivery before the labour starts. You will always find waiting mothers there whenever you visit. The most challenging during the stay there is that there are no beds nor matressess, and no maintenance done.
Sept 2018 |  | Nambazo HC | Construction of a kitchen for the maternity waiting home |  |  | Everything went on well in terms of community contribution and builder. | The kitchen is in use currently as women wait for the labour. They prepare their food as they sleep in the waiting shelter. This helps them to stay at the facility as they wait for the labour, mostly people coming from far like many from Mozambique because it's the closest facility.
Oct 2018 |  | Kalinde HC | Draining of the latrine |  |  | The whole job was done respectively. | It was done and the toilets were in use that time but now the toilets are in delapidated state and stopped to be used.
Aug 2019 |  | Nambazo HC | Rehabilitation of Njaro VC |  |  | The whole job was done respectively, only challenge was the transportation of materials because we used the manual local boats and the journeys lasted almost the whole day. | The Njalo VC is the only health facility that is currently on the Island. The village clinic is meant for the under 5 which makes the community to be not happy with the facility as they want it to treat every one who is sick at the Island. The facility has also difficult problem when getting supplies as they order from Nambazo health centre. The structure is in good state with availability of HSA during the time of evaluation.
Sept 2019 | Dec 2020 | Nambazo HC | Construction of Dindi VC | 1,600,000 |  | Followed a needs assessment in April 2019. Many problems with the builder, who lowered his labour fees to get the contract, but soon found himself unable to pay his workers. Construction took eight months instead of three. Opening was delayed because the HSA didn't want to move anymore, and the DHO wanted to make an official handover ceremony in the presence of the District Commissioner, which is very long to organize. The community did their part in contributing the sand and burnt bricks as well as the provision of store room for keeping construction materials. | Dindi VC is operational, the HSA stays there and provides the services. The site is also being used for the CMAs to provide midwifery services such as ANC, family Planning and postnatal services. GAIA (health services NGO) also use facility as an outreach site to provide health services including consultation. Renovation was also done by IA, they procured 2 doors after the originals were destroyed by termites.
Nov 2019 | Jan 2020 | Kalinde HC | Construction of Khudzupa OC shelter |  |  | When Inter Aide did the needs assessment in Kalinde, Khudzupa community indicated that they were very interested in building a shelter for outreach clinics. Construction began in November 2019 and lasted approximately 3 months, it took along time to finish and the shelter did not last for a long time because it started developing more cracks as the identified place has the bad soil texture which could not hold stucture for a long period of time. This site was identfied by the village headman and community. The store room for keeping materials was provided by the community as well as the store keeper was chosen by the community members from the village. | The construction was completed but started collapsing before being in use.
Dec 2019 |  | Kalinde HC | Construction of Kalinde HC incinerator and placenta pit | 600 |  | The construction of incinerator and placenta pit at Kalinde was done by Inte Aide CHP and the community around Kalinde since the community contributed burnt bricks, sand and the provision of store room for keeping construction material. The store keeper was chosen from among the HCMC. | These constructions are in good condition and in use. The OPD and the maternity depend on these two structures for waste management.
Sept 2019 | Feb 2022 | Kalinde HC | Construction of the maternity | 7,400,000 |  | 2019: authorisation from the district to follow our community lead approach for the construction of the maternity ward. Design validated by the Director of Public Work and MoU signed in September. IA is responsible for the construction, the DHO and the District will be responsible to provide the equipment. Beginning 2020: three builders to submit a bill of quantity, quotations for all the materials, discussion with the different stakeholders, choose to do the foundation with cement blocks and not with the local bricks: sustainability of the building and to not promote deforestation in the area. Phalombe District lent us two machines for the moulding of these blocks. The community was supported by the MP for Kalinde area. He gave money for the quarry stones and help with his truck to transport river sand and bricks. The community organize to bring sand, water and bricks for the walls. Total contribution of Kalinde community: 3,328,000 MKW (around 3 986 euros). April 2020: stat of construction with the moulding blocks May 2020: the foundations were finished and they started to build the wall. Oct 2020: construction completed, not opening due to lack of a waiting mothers’ shelter, their kitchen and bathrooms. MOU did not include these facilities but questions arose when the head of nursing/midwifery department was invited for inspection and approval. Additional MKW 310,000 to construct a kitchen and a bathroom. District council constructed another shelter, a kitchen and a two door bathroom. IA donated two delivery beds, connected water to the maternity, supported the MOH in maintenance of borehole, fixed electric water pump. With delay, mothers of Kalinde area continued to deliver at Migowi HC with nonreliable transport system, some have given birth at home or on their way. Migowi maternity unit has remained congested and staff overwhelmed. Feb 2022: launch of Kalinde Maternity attended by hundreds of villagers, Phalombe District dignitaries including the District Development council (DDC) and the political class headed by the area Member of Parliament a Mr. George Emilio Million. Since its launch in February, 585 mothers have been assisted to deliver in the HC. Although IA target of 100 deliveries per month has not been achieved, performance can be rated to be good at the moment. March 2022: facility was closed down due to lack of electric power caused by vandalism. Resolved when villagers contributed and bought the appliance that was missing on the transformer. April 2022: major sensitization meeting when the maternity reopened to mobilize community on utilization and demand for services at the maternity. It was resolved that under no circumstances should the maternity be closed again, instead staff should devise ways of sustaining service delivery. Oct 2022: Phalombe District Hospital was launched, Some villages previously utilising health services in Kalinde HC have therefore automatically moved to the District Hospital. Reduces the number of deliveries as the facility is serving these villages. Nov 2022: IA started building the incinerator and placenta pit. | The maternity is operational and in good state. There were problems with the roof as it was leaking but IA made some maintenances on it. Septic tank also collapsed and IA constructed new one. The facility is assisting the community in providing midwifery services hence improving their health status.
July 2020 | Oct 2020 | Nambazo HC | Construction toilet for patients at Dindi VC | 350 |  | The MOH provided all the essential medicines and equipment for a VC to run. Inter Aide provided petrol to support the DHO to transport Amoxicillin to the VC. The programme also donated a solar system and electric bulbs to light the VC at night and two buckets to manage waste. | The toilets are in good condition and full operational. This has helped the facility to be user friendly.
Mar 2021 |  | Kalinde HC | Technical assessment, blowing, water cleaning, pump test | 1,010,000 |  | To finalize the maternity. The blowing of water pump was tried but because the pump was stuck down the borehole it was difficult to remove the pump. | This was done and pump was installed later hence helped to supply water to the maternity unit.
Apr 2021 |  | Kalinde HC | Borehole connection for the maternity | 375 |  | There was a borehole just near the Maternity wing which was being used by both the community and the patients guardians. The HCMC, the GHV and other VHs conducted a meeting to discuss the idea of removing the Afridev pump and install the electric pump so that the pipes could be connected to the water tank in order for the Maternity to have running water in the facility. After they had agreed, the Kapitapa Bore hole contractor was given a contract to do the whole job. | Itt was done and now the maternity has water available for the services provided, because no availability of water will lead to the facility being closed.
Apr 2021 |  | Kalinde HC | Pumping test, electrical pump installation | 2,231,732 |  | To finalize the maternity. After the contractor had finished the pump installation and connection of the pipes from the pump to water tank, the pumping test was done as well as another one in the Maternity wing to see if the water was coming out of the taps, toilets and showers in bathrooms and the facility had running water. | It was done and now in operation
Apr 2021 |  | Nambiti HP | 2 toilets | 1,330,000 |  | Two doors and storage were fixed and six locks donated to ensure the doors are under key and lock. Donations included four chairs and two tables currently stationed at the health posts. Apart from this, two separate latrines were constructed in June 2021 to replace the one that was filled up and near collapsing. | Toilets were constructed and functioned for years before the doors being destroyed by unknown people. The doors have been fixed now this year by GAIA organisation.
May 2021 |  | Kalinde HC | 2 sinks and curtain rails for maternity | 110 |  | Materials were provided by Inter Aide Office. | It was done and useful for the operation of the maternity.
May 2021 |  | Kalinde HC | 2 toilets, shower, fixing of the placenta pit, filling and plastering for the maternity | 385 |  | Materials were provided by Inter Aide Office. | It was done and still in good condition as the maternity is operating.
Oct 2021 |  | Kalinde HC | Construction of a maternity waiting home's kitchen and bathroom at Kalinde by community | 90 |  | Condition imposed by the DHO to open the maternity, that was considered finished according to IA. It was constructed using the cement blocks which remained from the Maternity wing at Kalinde. The community contributed the roofing poles and sand. The builder was a local builder from the village. | The waiting home and bathroom were constructed and is helping the mothers at the facility during labour waiting and the delivery.
May 2022 | July 2022 | Nambazo HC | Placenta pit | 1,800,000 |  | Follows the collapse of the old one. All stakeholders were brought on board in the spirit of participation. The process begun with an initial meeting that was held in April 2022, with participants from the HCMC, ADC, in charge and maternity unit in charge and CSFC Programme Officer (PO). In this meeting, the budget was read to participants and community informed on their responsibility. Other meetings lead to contribution of river sand, bricks and quarry stone. Inter Aide procured all the remaining building materials that was listed in the BQ and paid labour charges. CSFC was constantly present onsite to monitor progress and to keep mobilizing the community on participation and project ownership while the MOH through the HC staff provided crucial needed supervision. Community contribution for the newly constructed placenta pit MKW621,000 Quarry stone-7 tones-Mkw 126,000 Bricks-20,000-Mkw 250,000 River sand-20 lories-Mkw 245,000 | The placenta pit was constructed and still in good condition.
July 2022 |  | Nambazo HC | Water connection | 190 |  | Support to the MOH to connect pipes into the outpatient and maternity departments of the health centre to improve hygiene of users and increase staff effort in infection prevention at their work place. | Nambazo had no water inside the maternity unit. IA connected the available water outside the maternity to be used inside as running water is the recommended for each maternity unit. This has improved infection prevention as well as waste management. Nambazo is the health centre with the most number of deliveries in the district.
Jun 2023 | Aug 23 | Chiringa maternity | Construction of a placenta pit and incinerator | 8,928,444 |  | IA adopted a new technology where soil sand blocks were used as opposed to the burnt bricks to prevent loss of forest cover in the district. Chiringa Maternity in March 2023 presented some of the immediate priority needs that had to be responded to. The facility had its Wash facilities dilapidated especially the filled up placenta pit and incinerator. The two were worsened by the occurrence of the cyclone Freddie. In consultation with the MOH, IA settled on constructing a new placenta pit and an incinerator to maintain sanitation in the facility and user dignity. Approved designs for the placenta pit, ash pit and incinerator were provided by the Ministry while Inter Aide collected quotations and Bill of quantities from willing builders. This time, IA adopted a new technology where soil sand blocks were used as opposed to the burnt bricks to prevent loss of forest cover in the district. This technology therefore required better skills in terms of mixing ratios. Among three local builders in Phalombe, only one provided a sample calculation on mixing sand, soil and cement to mould such bricks. He however missed out on the ratios, therefore Irritech Water Solution, a construction company was preferred as they also quoted the list cost of the two construction. Several meetings were conducted to bring on board all stakeholders including relevant MOH departments and community. A MOU was drafted and signed by all stakeholders involved. The project was completed and handed over to MOH and community in August 2023. Community participation in Chiringa Maternity construction was very poor because they resisted the builder whom they thought was not from Phalombe. The Local builders were very expensive and their quotations doubled what Irritech quoted for the entire project. This prompted the programme to sort for an external construction company from Blantyre who delivered very impressive result. | The maternity unit has modern placenta pit and incinerator after the completion of this construction. The previous placenta pit was full and the incinerator was in delapidated state. This has improved services delivery at the facility as the maternity can not work without placenta pit and incinerator.
Sept 2023 |  | Nambazo HC | Rehabilitation of the maternity roof |  |  | After cyclone Freddy. Nambazo is one of the health facilities that was affected by the March 2023 Cyclone Freddie. The Maternity Unit roof was left leaking especially in ANC, PNC and labour wards. Inter Aide supported the DHO by paying and facilitating a local builder who repaired the roof. At Dindi village clinic, two doors were had been destroyed by termites and needed replacement. The HSA in charge of the clinic was advised to mobilize the community through the Village Clinic Management Committee to replace and fix one door that was procured by the organization. Response from the community was positive and the two doors were perfectly fixed. In addition, the community has donated one bed that is used for examination of mothers at ANC and Postnatal clinic and constructed a shade which is now used as under five clinics. As such, health service provision at Dindi has been expanded from only under-five children consultations to many others. COmmunity participation MKW150,000 River sand-3 tons-Mkw 45,000 Quarry stone-3 tons-Mkw 105,000 | This was done as the maternity unit was leaking there by bringing unfavorable environment for labour and delivery during the rain season.
Oct 2023 |  | ? | Construction/rehabilitation of Nthambula VC (+HSA house ?) |  |  | Following the continuous needs assessment and monitoring of functioning village clinics, IA has been lobbying for opening of more VCs to increase patient and client accessibility and improve on health seeking behaviour of communities in Phalombe. Nthambula VC is one of the new clinics opened in September 2022, with a HSA trained with support from World Vision International but unable to relocate to the catchment area due to lack of suitable housing. A HSA house still stood in the Under Five clinic compound so Inter Aide and CSC with community mobilization repaired the house. IA procured cement, iron sheets and nails. The community contributed of burnt bricks, river sand and other small materials that were necessary for the repair works and wrote a letter to the area MP requesting for support in buying some building materials and payment of labour by a local builder. With this, they managed to secure a total amount of 400,000mkw that was used to pay the local builder. This entire activity came to completion in October 2023 enabling the HSA to move in. Inter Aide supported the MOH to fuel a truck that relocated the HSA to Nthambula. Community contribution on Nthambula project total 1,167,000MKW Local builder labour charges-Mkw 400,000 Burnt Bricks-1500 pcs-Mkw 120,000 River sand-10 tons-Mkw 15,000 Land contributed by community-Mkw 1,000,000 | The rehabilitation and construction of this village clinic has trigered the H S A to relocate to the area and start providing under five consultations to the area. This has reduced hours before a child access medical care as Nambazo is far from Nthambula. The only complaint raised by the community and service provider is the use of old iron sheets during the renovation as those leaks during the rains.
Jun 23 | Jan 26 | Kalinde | Construction/rehabilitation of Julius VC |  |  | The HSA house was swept away by the raging floods caused by cyclone Freddie. The staff lost all his household personal items including the drug box and medical equipment, as he operated from his own house. The loss did not discourage the HSA who resolved into participating in providing lifesaving services in the camp where he sort shelter for his family. This motivated IA to find a house within the area and pay rent for five months. Naminga Community in June 2023 moulded bricks and started searching for firewood for burning the bricks. The committee reached an agreement to construct a sizeable house (9 x 5.5) according to their financial ability. IA initially budgeted for 33 bags of cement, 36 pieces of iron sheets (10ft) and eight pieces of 7ft iron sheets. An additional 30 bags of Cement and timber costing 768,240 Mkw were procured and delivered to Naminga according to stages of construction. The area MP supported the Community’s request by paying the local builder’s labour charges, buying doors and windows to enable completion. This project took longer because of shortage of firewood for burning moulded bricks and absenteeism of the builder who was imposed by their MP. Community contribution for Naminga HSA house total MKw 2,626,000 Land donation by community-1 hectre-Mkw 1,000,000 Bricks-12,000-Mkw 96,000 River sand-10 tons-Mkw 150,000 Firewood for burning bricks and labour-Mkw 100,000 Local builder labour charges-Mkw 800,000 Steel bars for windows-2 Pcs-Mkw 30,000 Doors complete with frames-4 pcs-Mkw 300,000 | This Julis vc was constructed and now operational with the availability of H S A at the site. However, additional client shelter is needed as the facility is used as H S A house. The verander is too small to be used during the rainy season.
Dec 2023 |  | Gogo Nazombe HC | Double door latrines construction | 3,000,000 |  | On completion and hand over of Chiringa Maternity construction , the next priority was Two latrines for Gogo Nazombe Health centre. Following lengthy consultations between the DHMT, DHO Maintenance team, Local builders and Inter Aide, the team settled on constructing a double door latrine as opposed to two separate latrines that would have costed a lot of money. Inter Aide construction procedure was followed and the programme settled on Davie Kang’omawhose labour cost was more affordable. Several sensitization and mobilization meetings were held with the community leadership to notify of the project, spell out community role in participation and what community can contribute towards the project. This project took longer to start off as the community was going through lots of inflation shocks and food commodities had skyrocketed. They were unable to raise enough fund to procure river sand and quarry stone. However, the project started off late December 2023 and was at foundation level by end of the year. The community contribution was slow especialiy the contribution of quarry stones | This is the latest latrines that the facility has and depend mostly on it. It is being used for both staff and patients.
Jun 24 |  | Chiringa maternity | Water connection | 850 |  | Chiringa water connection contract was awarded to Eagle water solutions who managed to fix the pump and pipe connections to the water tank and the Maternity wing. Finally the facility started using tap water. | This was done and now the maternity has running water. The problems reported are sinks installed which are loose mostly to the mounted walls. No rehabilitation done.
Nov 2024 |  | Gogo Nazombe HC | Rehabilitation of the maternity | 9,825,000 |  | Circa 30 000 000 mkw. First meetinf at T/A's Office, second meeting was the orientation on stores management that took place at Gogo Nazombe Health Center conducted by IA staff and this meeting involved the Health center in-charge and HCMC. The store keeper was selected from the group on the same day. | The rehabilitation was completed in 2025 . No water supply and no electricity connected inside the maternity. Some materilas such as beds for delivery and postnatal were delivered. Efforts to restore water did not yield results.DHO and IA need to workout on this maternity to open.
February 2025 |  | Chiringa maternity | Water tower and connection of the water system | 11,212,250 |  | Contract was awarded to Dave Kang'oma who managed to mould the cement blocks for constructing the tower. The ADC chair played a very important role by mobilising the village heads and community to bring sand to Chiringa construction site to help much on moulding blocks and building the tower. | The water tower was finalised and connected to the pump sytem and supplied water to the maternity. Now the tank has deloped a crack which makes it unable to hold water. Currently , they are using another vtank installed by another local organinisation at a separate tower. DHO and IA need to discuss the wayforward about the tank replacement.
June 2025 | Jan 26 | Naminga | Pit latrine and bathroom at Julius VC | 230 |  | This was a community driven construction and Inter Aide only participated in providing the Ironsheets, cement, roofing nails and iron steel bars. | Construction was completed but only being used by the provider and not the clients.
May 2025 | Sept 2025 | Kalinde HC | Maternity sceptic tank | 16,517,051 |  | The contract was awarded to Dave Kang'oma to build the septic tank using cement blocks. The community also took part in contributing river sand and quarry stones. | The septic tank was constructed by IA after the colapsing of the previous tank. The huge new tank is now functioning as maternity waste are desposed in it. This has improved waste management issues at the facility and removing the risk for closure because the nurses and midwives council can not allow the maternity to operate without the septick tank.